## Sheet1
CONTROL STRIP - always visible | [5 empty] | INPUTS - type dates |  |  | AUDIT - Excel fills |  |  | READY | DEV REQUESTS | [5 empty] | QA REQUESTS | [5 empty] | PROD REQUESTS | [5 empty] | RELEASE GOVERNANCE | [6 empty] | VALIDATION
Application | Responsible PM | Sprint | Overall Status | Next Action | Next Action Date | Sprint Start | Sprint End | Release Date | Effective Sprint Start | Effective Sprint End | Effective Release Date | App Ready By | Dev R-Task | Dev R-Task Status | Dev OUR | Dev OUR Status | Dev Service Request | Dev SR Status | QA R-Task | QA R-Task Status | QA OUR | QA OUR Status | QA Service Request | QA SR Status | Prod R-Task | Prod R-Task Status | Prod OUR | Prod OUR Status | Prod Service Request | Prod SR Status | CAB Date | CAB Status | Code Review Date | Code Review Status | Code Review Invite | CR Invite Status | Release Status | Validation / Notes
App-SprintOnly | Subash | Sprint 14 | In Progress | QA R-Task | 2026-08-12 | 2026-08-24 | 2026-09-04 |  | 2026-08-24 | 2026-09-04 | 2026-09-03 | 2026-08-21 | 2026-09-12 | Completed | 2026-09-14 | In Progress | 2026-09-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-09-02 |  | 2026-08-31 |  | 2026-08-27 |  |  | One or more raise-by dates are in the past and not completed
App-ASDFASDFSprintOnly | Abishek | Sprint 14 | In Progress | QA R-Task | 2026-08-12 | 2026-08-24 | 2026-09-04 |  | 2026-08-24 | 2026-09-04 | 2026-09-03 | 2026-08-21 | 2026-08-12 | Completed | 2026-08-14 | In Progress | 2026-08-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-09-02 |  | 2026-08-31 |  | 2026-08-27 |  |  | One or more raise-by dates are in the past and not completed
ASDF | shrinath | Sprint 14 | In Progress | QA R-Task | 2026-08-12 | 2026-08-24 | 2026-09-04 |  | 2026-08-24 | 2026-09-04 | 2026-09-03 | 2026-08-21 | 2026-08-12 | Completed | 2026-08-14 | In Progress | 2026-08-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-09-02 |  | 2026-08-31 |  | 2026-08-27 |  |  | One or more raise-by dates are in the past and not completed
SDFHKJASDFASDF | ishan | Sprint 14 | In Progress | QA R-Task | 2026-08-12 | 2026-08-24 | 2026-09-04 |  | 2026-08-24 | 2026-09-04 | 2026-09-03 | 2026-08-21 | 2026-08-12 | Completed | 2026-08-14 | In Progress | 2026-08-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-09-02 |  | 2026-08-31 |  | 2026-08-27 |  |  | One or more raise-by dates are in the past and not completed
App-SprintOnly - 2 | Sabareesh | Sprint 14 | In Progress | QA R-Task | 2026-08-12 | 2026-08-24 | 2026-09-04 |  | 2026-08-24 | 2026-09-04 | 2026-09-03 | 2026-08-21 | 2026-08-12 | Completed | 2026-08-14 | In Progress | 2026-08-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-09-02 |  | 2026-08-31 |  | 2026-08-27 |  |  | One or more raise-by dates are in the past and not completed
this is 2nd project | Subash | Sprint 14 | In Progress | QA R-Task | 2026-08-12 | 2026-08-24 | 2026-09-04 |  | 2026-08-24 | 2026-09-04 | 2026-09-03 | 2026-08-21 | 2026-09-12 | Completed | 2026-09-14 | In Progress | 2026-09-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-08-12 |  | 2026-08-14 |  | 2026-08-17 |  | 2026-09-02 |  | 2026-08-31 |  | 2026-08-27 |  |  | One or more raise-by dates are in the past and not completed

## Sheet2
Name | Email
Abishek | amuralidharan@randomtrees.com
Subash | sbandari@randomtrees.com
ishan | ibhattacharjee@randomtrees.com
shrinath | smuralikrishna@randomtrees.com
Subash | sbandari@randomtrees.com
Sabareesh | skrishna@randomtrees.com