## Dashboard
Application access & release tracker | [5 empty] | Formulas only. Update yellow cells on Tracker. Sheet is locked.
As of | 2026-08-21 |  | KPIs use current Tracker columns (File Type Z / Frequency AF shared). TBD is separate from N/A. Reopen/recalc if numbers look stale.
Applications |  | Overdue tickets |  | Blocked |  | Due in 7 days |  | In progress |  | Fully ready |  | overdue (days) |  | Raised on time
43 |  | 205 |  | 0 |  | 0 |  | 24 |  | 0 |  | 35 |  | 100
Apps with a name filled |  | Date in the past and status not Completed |  | Requests marked Blocked |  | Raise-by in the next week, not Completed |  | Tickets marked In Progress |  | Every dated request Completed |  | Days past raise-by among open requests. Increases daily until Completed. |  | Requests with Raised On filled on or before the raise-by date.
Apps overdue - worst first (days overdue keeps increasing until Completed) | [5 empty] | Where work is stuck - by request type
Application | Sprint | Overall Status | Next Action | Next Action Date | Days overdue | Request type | Overdue | Due in 7 days | Blocked | In Progress | Pending | Completed | Overdue bar
Ecosys | Sprint 17 | In Progress | Dev File R-Task | 2026-07-17 | 35 | Dev R-Task | 10 | 0 | 0 | 0 | 43 | 0 | ¦¦¦¦¦¦¦¦¦¦
ALLOCATIONS | Sprint 17 | In Progress | Dev R-Task | 2026-07-17 | 35 | Dev OUR | 10 | 0 | 0 | 0 | 14 | 7 | ¦¦¦¦¦¦¦¦¦¦
AUDIT REPORTS | Sprint 17 | In Progress | Prod OUR | 2026-07-21 | 31 | Dev Service Request | 11 | 0 | 0 | 1 | 43 | 0 | ¦¦¦¦¦¦¦¦¦¦¦
EDDS | Sprint 17 | In Progress | Prod OUR | 2026-07-21 | 31 | Dev File R-Task | 4 | 0 | 0 | 1 | 0 | 0 | ¦¦¦¦
EPM_BALANCES | Sprint 17 | In Progress | Prod OUR | 2026-07-21 | 31 | QA R-Task | 10 | 0 | 0 | 0 | 0 | 33 | ¦¦¦¦¦¦¦¦¦¦
EPM_DIM_NOD | Sprint 17 | In Progress | Prod OUR | 2026-07-21 | 31 | QA OUR | 10 | 0 | 0 | 0 | 43 | 0 | ¦¦¦¦¦¦¦¦¦¦
EPM_UI PUSH | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | QA Service Request | 10 | 0 | 0 | 0 | 0 | 0 | ¦¦¦¦¦¦¦¦¦¦
AR80 | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | QA File R-Task | 4 | 0 | 0 | 0 | 4 | 0 | ¦¦¦¦
BI80 | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | Prod R-Task | 10 | 0 | 0 | 0 | 0 | 0 | ¦¦¦¦¦¦¦¦¦¦
CBP | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | Prod OUR | 43 | 0 | 0 | 0 | 43 | 0 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
CI | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | Prod Service Request | 43 | 0 | 0 | 0 | 0 | 0 | ¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦¦
CI_MART | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | Prod File R-Task | 4 | 0 | 0 | 0 | 190 | 40
[6 empty] | Sprint Readiness | 36 | 0 | 0
[6 empty] | CAB | 0 | 0 | 0
[6 empty] | Code Review | 0 | 0 | 0
[6 empty] | Code Review Invite | 0 | 0 | 0
Formulas:
Blocked = IF([Applications] = "", "", IFERROR(INDEX(Tracker!$F3:F100, MATCH(SINGLE(AGGREGATE(15, 6, Tracker!$CG3:CG100, 1)), Tracker!$CG3:CG100, 0)), ""))

## Tracker
CONTROL STRIP - always visible | [6 empty] | INPUTS - type dates |  |  | AUDIT - Excel fills |  |  | READY / READINESS |  |  | DEV DB REQUESTS | [8 empty] | DEV FILE REQUESTS | [6 empty] | QA DB REQUESTS | [8 empty] | QA FILE REQUESTS |  |  |  |  | PROD DB REQUESTS | [8 empty] | PROD FILE REQUESTS |  |  |  |  | RELEASE GOVERNANCE | [6 empty] | VALIDATION
Application | Responsible PM | Sprint | Overall Status | Next Action | Next Action Date | Days Overdue | Sprint Start | Sprint End | Release Date | Effective Sprint Start | Effective Sprint End | Effective Release Date | App Ready By | Sprint Readiness Date | Sprint Readiness Status | Dev R-Task | Raised On | Dev R-Task Status | Dev OUR | Raised On | Dev OUR Status | Dev Service Request | Raised On | Dev SR Status | File Type (all envs) | Dev File R-Task | Raised On | Dev File R-Task Status | IAM | Ownership Identified | Frequency (all envs) | QA R-Task | Raised On | QA R-Task Status | QA OUR | Raised On | QA OUR Status | QA Service Request | Raised On | QA SR Status | QA File R-Task | Raised On | QA File R-Task Status | IAM | Ownership Identified | Prod R-Task | Raised On | Prod R-Task Status | Prod OUR | Raised On | Prod OUR Status | Prod Service Request | Raised On | Prod SR Status | Prod File R-Task | Raised On | Prod File R-Task Status | IAM | Ownership Identified | CAB Date | CAB Status | Code Review Date | Code Review Status | Code Review Invite | CR Invite Status | Release Status | Validation / Notes
CI_MART | Sharath Kotha | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | Completed | 2026-07-17 | 2026-07-30 | Completed | 2026-07-21 | 2026-07-17 | Completed | 2026-07-22 | 2026-07-17 | Completed | N/A | [5 empty] | N/A | 2026-07-17 | 2026-07-22 | Completed | 2026-07-21 | 2026-07-22 | Completed | 2026-07-22 | 2026-07-22 | Completed | [5 empty] | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46224 | 46225 |  |  | 46293 | 46297 | 46300 | 0.032258
CI | Sharath Kotha | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | Completed | 2026-07-17 | 2026-07-30 | Completed | 2026-07-21 | 2026-07-17 | Completed | 2026-07-22 | 2026-07-17 | Completed | N/A | [5 empty] | N/A | 2026-07-17 | 2026-07-22 | Completed | 2026-07-21 | 2026-07-22 | Completed | 2026-07-22 | 2026-07-22 | Completed | [5 empty] | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46224 | 46225 |  |  | 46293 | 46297 | 46300 | 0.032258
CBP | Sharath Kotha | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | Completed | 2026-07-17 | 2026-07-30 | Completed | 2026-07-21 | 2026-07-17 | Completed | 2026-07-22 | 2026-07-17 | Completed | N/A | [5 empty] | N/A | 2026-07-17 | 2026-07-22 | Completed | 2026-07-21 | 2026-07-22 | Completed | 2026-07-22 | 2026-07-22 | Completed | [5 empty] | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46224 | 46225 |  |  | 46293 | 46297 | 46300 | 0.032258
BI80 | Sharath Kotha | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | Completed | 2026-07-17 | 2026-07-30 | Completed | 2026-07-21 | 2026-07-17 | Completed | 2026-07-22 | 2026-07-17 | Completed | N/A | [5 empty] | N/A | 2026-07-17 | 2026-07-22 | Completed | 2026-07-21 | 2026-07-22 | Completed | 2026-07-22 | 2026-07-22 | Completed | [5 empty] | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46224 | 46225 |  |  | 46293 | 46297 | 46300 | 0.032258
AR80 | Sharath Kotha | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | Completed | 2026-07-17 | 2026-08-11 | Completed | 2026-07-21 | 2026-08-11 | Completed | 2026-07-22 | 2026-08-11 | Completed | N/A |  | 2026-08-11 | Completed | N/A | No | N/A | 2026-07-17 | 2026-07-22 | Completed | 2026-07-21 | 2026-07-22 | Completed | 2026-07-22 | 2026-07-22 | Completed | [5 empty] | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46224 | 46225 |  |  | 46293 | 46297 | 46300 | 0.032258
ALLOCATIONS | Sharath Kotha | Sprint 17 | In Progress | Dev R-Task | 2026-07-17 | 35 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | Completed | 2026-07-17 |  | Yet to start | 2026-07-21 |  | Yet to start | 2026-07-22 |  | Yet to start |  |  |  | Yet to start |  |  |  | 2026-07-17 | 2026-07-22 | In Progress | 2026-07-21 | 2026-07-22 | Yet to start | 2026-07-22 | 2026-07-22 | Yet to start | [5 empty] | 2026-07-17 |  | Yet to start | 2026-07-21 |  |  | 2026-07-22 | [5 empty] | Yes | Yes | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | 46220 | 46224 | 46225 |  | 46220 | 46224 | 46225 |  | 46220 | 46224 | 46225 |  |  | 46293 | 46297 | 46300 | 0.028571
EPM_UI PUSH | Sharath Kotha | Sprint 17 | Yet to start | Prod OUR | 2026-07-21 | 31 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | Completed | 2026-07-17 | 2026-07-30 | Completed | 2026-07-21 | 2026-07-17 | Completed | 2026-07-22 | 2026-07-17 | Completed | N/A | [5 empty] | N/A | 2026-07-17 | 2026-07-22 | Completed | 2026-07-21 | 2026-07-22 | Completed | 2026-07-22 | 2026-07-22 | Completed | [5 empty] | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46224 | 46225 |  |  | 46293 | 46297 | 46300 | 0.032258
EPM_DIM_NOD | Sharath Kotha | Sprint 17 | In Progress | Prod OUR | 2026-07-21 | 31 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | In Progress | 2026-07-17 | 2026-08-12 | Completed | 2026-07-21 | 2026-07-31 | Completed | 2026-07-22 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-17 | 2026-08-05 | Completed | 2026-07-21 | 2026-08-05 | Completed | 2026-07-22 | 2026-08-05 | Completed | [5 empty] | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46224 | 46225 |  | 46230 | 46293 | 46297 | 46300 | 0.032258
EPM_BALANCES | Sharath Kotha | Sprint 17 | In Progress | Prod OUR | 2026-07-21 | 31 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | In Progress | 2026-07-17 | 2026-08-12 | Completed | 2026-07-21 | 2026-07-31 | Completed | 2026-07-22 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-17 | 2026-08-05 | Completed | 2026-07-21 | 2026-08-05 | Completed | 2026-07-22 | 2026-08-05 | Completed | [5 empty] | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46224 | 46225 |  | 46230 | 46293 | 46297 | 46300 | 0.032258
EDDS | Sharath Kotha | Sprint 17 | In Progress | Prod OUR | 2026-07-21 | 31 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | In Progress | 2026-07-17 | 2026-08-12 | Completed | 2026-07-21 | 2026-07-31 | Completed | 2026-07-22 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-17 | 2026-08-05 | Completed | 2026-07-21 | 2026-08-05 | Completed | 2026-07-22 | 2026-08-05 | Completed | [5 empty] | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46224 | 46225 |  | 46230 | 46293 | 46297 | 46300 | 0.032258
Ecosys | Sharath Kotha | Sprint 17 | In Progress | Dev File R-Task | 2026-07-17 | 35 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | In Progress | 2026-07-17 | 2026-08-12 | Completed | 2026-07-21 | 2026-07-31 | Completed | 2026-07-22 | 2026-07-31 | Completed | FTP | 2026-07-17 | [5 empty] | 2026-07-17 | 2026-08-05 | Completed | 2026-07-21 | 2026-08-05 | Completed | 2026-07-22 | 2026-08-05 | Completed | 2026-07-17 |  |  |  |  | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 |  |  | 2026-07-17 |  |  |  |  | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed |  |  |  | 46220 |  |  |  | 46220 |  | 46224 | 46225 | 46220 | 46230 | 46293 | 46297 | 46300 | 0.028571
AUDIT REPORTS | Sharath Kotha | Sprint 17 | In Progress | Prod OUR | 2026-07-21 | 31 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-29 | 2026-08-11 | 2026-10-05 | 2026-07-28 | 2026-07-27 | In Progress | 2026-07-17 | 2026-08-12 | Completed | 2026-07-21 | 2026-07-31 | Completed | 2026-07-22 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-17 | 2026-08-05 | Completed | 2026-07-21 | 2026-08-05 | Completed | 2026-07-22 | 2026-08-05 | Completed | [5 empty] | 2026-07-17 |  | Completed | 2026-07-21 |  |  | 2026-07-22 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46224 | 46225 |  | 46230 | 46293 | 46297 | 46300 | 0.032258
FIN | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
FINDET_BUDGETS | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
FINREC | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
FOF_WORKIVA | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
GL80 | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
IKW | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
P2P | Sharath Kotha | Sprint 18 | In Progress | Dev File R-Task | 2026-07-31 | 21 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | In Progress | FTP | 2026-07-31 | [5 empty] | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | 2026-07-31 |  |  |  |  | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 |  |  | 2026-07-31 |  |  |  |  | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed |  |  | 46239 | 46234 |  |  |  | 46234 |  | 46238 | 46239 | 46234 | 46244 | 46293 | 46297 | 46300 | 0.047619
PC80 | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
PO80 | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
PSTREE_EPM | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
RAS | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
Real_Estate | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
SECURITY | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
TRIAD | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058823
UIBUDGETS | Sharath Kotha | Sprint 18 | In Progress | Dev File R-Task | 2026-07-31 | 21 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | FTP | 2026-07-31 | [5 empty] | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | 2026-07-31 |  |  |  |  | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 |  |  | 2026-07-31 |  |  |  |  | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed |  |  |  | 46234 |  |  |  | 46234 |  | 46238 | 46239 | 46234 | 46244 | 46293 | 46297 | 46300 | 0.047618
IKW_DWMS | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058822
LED | Sharath Kotha | Sprint 18 | In Progress | Prod OUR | 2026-08-04 | 17 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | In Progress | 2026-07-31 | 2026-08-12 | Completed | 2026-08-04 | 2026-07-31 | Completed | 2026-08-05 | 2026-07-31 | Completed | N/A | [5 empty] | N/A | 2026-07-31 | 2026-08-05 | Completed | 2026-08-04 | 2026-08-05 | Completed | 2026-08-05 | 2026-08-05 | Completed | [5 empty] | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed | [9 empty] | 46238 | 46239 |  | 46244 | 46293 | 46297 | 46300 | 0.058822
UI_PLANNER | Sharath Kotha | Sprint 18 | Yet to start | Dev File R-Task | 2026-07-31 | 21 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-12 | 2026-08-25 | 2026-10-05 | 2026-08-11 | 2026-08-10 | Yet to start | 2026-07-31 | 2026-08-18 | Completed | 2026-08-04 | 2026-08-14 | Completed | 2026-08-05 | 2026-08-14 | Completed | FTP | 2026-07-31 | [5 empty] | 2026-07-31 | 2026-08-19 | Completed | 2026-08-04 | 2026-08-19 | Completed | 2026-08-05 | 2026-08-19 | Completed | 2026-07-31 |  |  |  |  | 2026-07-31 |  | Completed | 2026-08-04 |  |  | 2026-08-05 |  |  | 2026-07-31 |  |  |  |  | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed |  |  |  | 46234 |  |  |  | 46234 |  | 46238 | 46239 | 46234 | 46244 | 46293 | 46297 | 46300 | 0.047618
FEL | Sharath Kotha | Sprint 19 | Yet to start | Prod OUR | 2026-08-18 | 3 | 2026-08-26 | 2026-09-08 | 2026-10-05 | 2026-08-26 | 2026-09-08 | 2026-10-05 | 2026-08-25 | 2026-08-24 | Yet to start | 2026-08-14 | 2026-08-18 | Completed | 2026-08-18 | 2026-08-14 | Completed | 2026-08-19 | 2026-08-14 | Completed | N/A | [5 empty] | N/A | 2026-08-14 | 2026-08-19 | Completed | 2026-08-18 | 2026-08-19 | Completed | 2026-08-19 | 2026-08-19 | Completed | [5 empty] | 2026-08-14 |  | Completed | 2026-08-18 |  |  | 2026-08-19 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed ¦ Sprint starts in under 10 days - raise access requests now | [9 empty] | 46252 | 46253 |  | 46258 | 46293 | 46297 | 46300 | 0.3333
Claims_Portal | Sharath Kotha | Sprint 19 | Yet to start | Prod OUR | 2026-08-18 | 3 | 2026-08-26 | 2026-09-08 | 2026-10-05 | 2026-08-26 | 2026-09-08 | 2026-10-05 | 2026-08-25 | 2026-08-24 | Yet to start | 2026-08-14 | 2026-08-18 | Completed | 2026-08-18 | 2026-08-14 | Completed | 2026-08-19 | 2026-08-14 | Completed | N/A | [5 empty] | N/A | 2026-08-14 | 2026-08-19 | Completed | 2026-08-18 | 2026-08-19 | Completed | 2026-08-19 | 2026-08-19 | Completed | [5 empty] | 2026-08-14 |  | Completed | 2026-08-18 |  |  | 2026-08-19 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed ¦ Sprint starts in under 10 days - raise access requests now | [9 empty] | 46252 | 46253 |  | 46258 | 46293 | 46297 | 46300 | 0.3333
DWMR_DM | Sharath Kotha | Sprint 19 | Yet to start | Prod OUR | 2026-08-18 | 3 | 2026-08-26 | 2026-09-08 | 2026-10-05 | 2026-08-26 | 2026-09-08 | 2026-10-05 | 2026-08-25 | 2026-08-24 | Yet to start | 2026-08-14 | 2026-08-18 | Completed | 2026-08-18 | 2026-08-14 | Completed | 2026-08-19 | 2026-08-14 | Completed | N/A | [5 empty] | N/A | 2026-08-14 | 2026-08-19 | Completed | 2026-08-18 | 2026-08-19 | Completed | 2026-08-19 | 2026-08-19 | Completed | [5 empty] | 2026-08-14 |  | Completed | 2026-08-18 |  |  | 2026-08-19 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered ¦ One or more raise-by dates are in the past and not completed ¦ Sprint starts in under 10 days - raise access requests now | [9 empty] | 46252 | 46253 |  | 46258 | 46293 | 46297 | 46300 | 0.33329
MISO | Sharath Kotha | Sprint 20 | Yet to start | Prod OUR | 2026-09-01 | 0 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-08 | 2026-09-07 | Yet to start | 2026-08-28 | 2026-08-18 | Completed | 2026-09-01 | 2026-08-14 | Completed | 2026-09-02 | 2026-08-14 | Completed | N/A | [5 empty] | N/A | 2026-08-28 | 2026-08-19 | Completed | 2026-09-01 | 2026-08-19 | Completed | 2026-09-02 | 2026-08-19 | Completed | [5 empty] | 2026-08-28 |  | Completed | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered | [9 empty] | 46266 | 46267 |  | 46272 | 46293 | 46297 | 46300 | 47266.0004
Pasta | Sharath Kotha | Sprint 20 | Yet to start | Dev R-Task | 2026-08-28 | 0 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-08 | 2026-09-07 | Yet to start | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [9 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46272 | 46293 | 46297 | 46300 | 47262.0004
GADS | Sharath Kotha | Sprint 20 | Yet to start | Dev R-Task | 2026-08-28 | 0 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-08 | 2026-09-07 | Yet to start | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [9 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46272 | 46293 | 46297 | 46300 | 47262.0004
GENMART | Sharath Kotha | Sprint 20 | Yet to start | Dev R-Task | 2026-08-28 | 0 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-08 | 2026-09-07 | Yet to start | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [9 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46272 | 46293 | 46297 | 46300 | 47262.0004
TELECOM_CEB | Sharath Kotha | Sprint 20 | Yet to start | Dev R-Task | 2026-08-28 | 0 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-08 | 2026-09-07 | Yet to start | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [9 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46272 | 46293 | 46297 | 46300 | 47262.0004
TPD | Sharath Kotha | Sprint 20 | Yet to start | Dev R-Task | 2026-08-28 | 0 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-08 | 2026-09-07 | Yet to start | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [9 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46272 | 46293 | 46297 | 46300 | 47262.0004
FIELD_MOBILITY | Sharath Kotha | Sprint 20 | Yet to start | Dev R-Task | 2026-08-28 | 0 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-08 | 2026-09-07 | Yet to start | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [9 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46272 | 46293 | 46297 | 46300 | 47262.0004
Conformed_Dimensions | Sharath Kotha | Sprint 20 | Yet to start | Dev R-Task | 2026-08-28 | 0 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-08 | 2026-09-07 | Yet to start | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [9 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46272 | 46293 | 46297 | 46300 | 47262.0004
Maximo_EDW-TDC | Sharath Kotha | Sprint 20 | Yet to start | Dev R-Task | 2026-08-28 | 0 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-08 | 2026-09-07 | Yet to start | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [9 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46272 | 46293 | 46297 | 46300 | 47262.0004
FACILITY | Sharath Kotha | Sprint 20 | Yet to start | Dev R-Task | 2026-08-28 | 0 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-09 | 2026-09-22 | 2026-10-05 | 2026-09-08 | 2026-09-07 | Yet to start | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [9 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-08-28 |  |  | 2026-09-01 |  |  | 2026-09-02 | [7 empty] | 2026-10-05 |  | 2026-10-02 |  | 2026-09-28 |  |  | Release must be Tuesday or Thursday ¦ Sprint Start is not a Monday - dates still calculated from the date entered | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46262 | 46266 | 46267 |  | 46272 | 46293 | 46297 | 46300 | 47262.0004
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
Formulas:
Next Action Date = IF([CONTROL STRIP - always visible]="","",IF(COUNT(BQ3:CF3)=0,"",MIN(BQ3:CF3)))
AUDIT - Excel fills = IF(ISNUMBER([INPUTS - type dates]),[INPUTS - type dates],IF(ISNUMBER([Effective Release Date]),[Effective Release Date]-WEEKDAY([Effective Release Date],2)+1-7,""))
Effective Sprint End = IF(ISNUMBER([Sprint End]),[Sprint End],IF(ISNUMBER([INPUTS - type dates]),WORKDAY([INPUTS - type dates],SprintWorkingDays-1),IF(ISNUMBER([AUDIT - Excel fills]),WORKDAY([AUDIT - Excel fills],SprintWorkingDays-1),"")))
READY / READINESS = IF(NOT(ISNUMBER([AUDIT - Excel fills])),"",WORKDAY([AUDIT - Excel fills],ReadyOffsetWD))
Sprint Readiness Date = IF(NOT(ISNUMBER([AUDIT - Excel fills])),"",WORKDAY([AUDIT - Excel fills],SprintReadinessOffsetWD))
DEV DB REQUESTS = IF([CONTROL STRIP - always visible]="","",IF([Dev OUR Status]="N/A",IF(NOT(ISNUMBER([Dev Service Request])),"",WORKDAY([Dev Service Request],RTSKOffsetFromOUR_WD)),IF(NOT(ISNUMBER([Dev OUR])),"",WORKDAY([Dev OUR],RTSKOffsetFromOUR_WD))))
Dev OUR = IF(OR([CONTROL STRIP - always visible]="",[Dev OUR Status]="N/A"),"",IF(NOT(ISNUMBER([Dev Service Request])),"",WORKDAY([Dev Service Request],OUROffsetFromSR_WD)))
Dev Service Request = IF(OR([CONTROL STRIP - always visible]="",NOT(ISNUMBER([AUDIT - Excel fills]))),"",WORKDAY([AUDIT - Excel fills],SROffsetFromStartWD))
QA DB REQUESTS = IF(NOT(ISNUMBER([DEV DB REQUESTS])),"",[DEV DB REQUESTS])
QA OUR = IF(OR([QA OUR Status]="N/A",NOT(ISNUMBER([Dev OUR]))),"",[Dev OUR])
QA Service Request = IF(NOT(ISNUMBER([Dev Service Request])),"",[Dev Service Request])
PROD DB REQUESTS = IF(NOT(ISNUMBER([DEV DB REQUESTS])),"",[DEV DB REQUESTS])
Prod OUR = IF(OR([Prod OUR Status]="N/A",NOT(ISNUMBER([Dev OUR]))),"",[Dev OUR])
Prod Service Request = IF(NOT(ISNUMBER([Dev Service Request])),"",[Dev Service Request])
Code Review Date = IF(NOT(ISNUMBER([RELEASE GOVERNANCE])),"",IF(WEEKDAY([RELEASE GOVERNANCE]-CodeReviewCalendarDays,2)>5,[RELEASE GOVERNANCE]-CodeReviewCalendarDays-(WEEKDAY([RELEASE GOVERNANCE]-CodeReviewCalendarDays,2)-5),[RELEASE GOVERNANCE]-CodeReviewCalendarDays))
Code Review Invite = IF(NOT(ISNUMBER([Code Review Date])),"",IF(WEEKDAY([Code Review Date]-CodeReviewInviteCalendarDays,2)>5,[Code Review Date]-CodeReviewInviteCalendarDays-(WEEKDAY([Code Review Date]-CodeReviewInviteCalendarDays,2)-5),[Code Review Date]-CodeReviewInviteCalendarDays))
Dev File R-Task = IF(OR([DEV FILE REQUESTS]="",[DEV FILE REQUESTS]="N/A"),"",IF(ISNUMBER([DEV DB REQUESTS]),[DEV DB REQUESTS],""))
QA FILE REQUESTS = IF(OR([DEV FILE REQUESTS]="",[DEV FILE REQUESTS]="N/A"),"",IF(ISNUMBER([QA DB REQUESTS]),[QA DB REQUESTS],""))
PROD FILE REQUESTS = IF(OR([DEV FILE REQUESTS]="",[DEV FILE REQUESTS]="N/A"),"",IF(ISNUMBER([PROD DB REQUESTS]),[PROD DB REQUESTS],""))
RELEASE GOVERNANCE = IF(OR([CONTROL STRIP - always visible]="",NOT(ISNUMBER([Effective Release Date])),AND(WEEKDAY([Effective Release Date],2)<>2,WEEKDAY([Effective Release Date],2)<>4)),"",WORKDAY([Effective Release Date],CABOffsetFromReleaseWD))

## Sprints
Sprint # | Sprint Start | Sprint End
SPRINT 13 | 2026-06-03 | 2026-06-16
SPRINT 14 | 2026-06-17 | 2026-06-30
SPRINT 15 | 2026-07-01 | 2026-07-14
SPRINT 16 | 2026-07-15 | 2026-07-28
SPRINT 17 | 2026-07-29 | 2026-08-11
SPRINT 18 | 2026-08-12 | 2026-08-25
SPRINT 19 | 2026-08-26 | 2026-09-08
SPRINT 20 | 2026-09-09 | 2026-09-22
SPRINT 21 | 2026-09-23 | 2026-10-06
SPRINT 22 | 2026-10-07 | 2026-10-20
SPRINT 23 | 2026-10-21 | 2026-11-03

## Config (hidden)
Lead-time parameters - change yellow values only
Parameter | Value | Meaning | Status list | File types | Frequency | IAM | Yes/No
SprintWorkingDays | 10 | Working days in a sprint when one side is blank (2-week default). | Yet to start | MP | Daily at 5:00 AM | Yes | Yes
ReadyOffsetWD | -1 | Working days from Effective Sprint Start to Ready By. Monday start -> previous Friday. | In Progress | FTP | Weekly (Mon at 12:00 AM) | No | No
SROffsetFromStartWD | -5 | Sprint start -> Service Request raise-by. Monday start -> previous Monday. | Blocked | Fileshare | Weekly (Thursday at 12:00 AM) | N/A
OUROffsetFromSR_WD | -1 | Service Request date -> OUR raise-by. SR Monday -> previous Friday. | Completed | API | Monthly (1st Monday at 4:00 AM)
RTSKOffsetFromOUR_WD | -2 | OUR -> R-Task. OUR Friday -> previous Wednesday (VP extra buffer). | N/A | Mount | Yearly
CABOffsetFromReleaseWD | -1 | Release -> CAB. Thu -> Wed; Tue -> Mon. | TBD | Source | Adhoc (on demand)
CodeReviewCalendarDays | 2 | Calendar days before CAB; weekend snaps to previous Friday. |  | MFT | N/A
CodeReviewInviteCalendarDays | 4 | Calendar days before Code Review to send invite email. |  | SFTP | TBD
Yellow cells are editable. Sheet is protected so formulas cannot be overwritten. Review > Unprotect Sheet if you must change structure (no password). Sequence: R-Task -> OUR -> Service Request. Releases Tue/Thu only. CAB Mon/Wed/Fri. |  |  |  | NFS
N/A
SprintWarningDays | 10 | Days before Effective Sprint Start to warn if requests not actioned. |  | TBD
N/A = not applicable (no file). TBD = type/frequency still to be decided (File R-Task still calculated).
SprintReadinessOffsetWD | -2 | Working days from Effective Sprint Start to sprint-readiness discussion. |  | Status TBD = pending decision; does not count as Completed/N/A.