## Dashboard
Application access & release tracker | [5 empty] | Formulas only. Update yellow cells on Tracker. Sheet is locked.
As of |  |  | Sprint calendar is on the Sprints sheet. File R-Task date copies the matching DB R-Task date. Overdue days grow until status is Completed. Enter Raised On when the ticket is submitted.
Applications |  | Overdue tickets |  | Blocked |  | Due in 7 days |  | In progress |  | Fully ready |  | Worst overdue (days) |  | Raised on time
Apps with a name filled |  | Date in the past and status not Completed |  | Requests marked Blocked |  | Raise-by in the next week, not Completed |  | Tickets marked In Progress |  | Every dated request Completed |  | Days past raise-by among open requests. Increases daily until Completed. |  | Requests with Raised On filled on or before the raise-by date.
Apps overdue - worst first (days overdue keeps increasing until Completed) | [5 empty] | Where work is stuck - by request type
Application | Sprint | Overall Status | Next Action | Next Action Date | Days overdue | Request type | Overdue | Due in 7 days | Blocked | In Progress | Pending | Completed | Overdue bar
Dev R-Task
Dev OUR
Dev Service Request
QA R-Task
QA OUR
QA Service Request
Prod R-Task
Prod OUR
Prod Service Request
Dev File R-Task
CAB
Code Review
Formulas:
Days overdue = IF(OR([Applications]="",NOT(ISNUMBER([Blocked]))),"",[Blocked]-TODAY())

## Tracker
CONTROL STRIP | [6 empty] | INPUTS - type dates |  |  | AUDIT - Excel fills |  |  | READY / READINESS |  |  | DEV DB REQUESTS | [8 empty] | DEV FILE REQUESTS | [6 empty] | QA DB REQUESTS | [8 empty] | QA FILE REQUESTS | [6 empty] | PROD DB REQUESTS | [8 empty] | PROD FILE REQUESTS | [6 empty] | RELEASE GOVERNANCE | [6 empty] | VALIDATION
Application | Responsible PM | Sprint | Overall Status | Next Action | Next Action Date | Days Overdue | Sprint Start | Sprint End | Release Date | Effective Sprint Start | Effective Sprint End | Effective Release Date | App Ready By | Sprint Readiness Date | Sprint Readiness Status | Dev R-Task | Raised On | Dev R-Task Status | Dev OUR | Raised On | Dev OUR Status | Dev Service Request | Raised On | Dev SR Status | File Type | Dev File R-Task | Raised On | Dev File R-Task Status | IAM | Ownership Identified | Frequency | QA R-Task | Raised On | QA R-Task Status | QA OUR | Raised On | QA OUR Status | QA Service Request | Raised On | QA SR Status | File Type | QA File R-Task | Raised On | QA File R-Task Status | IAM | Ownership Identified | Frequency | Prod R-Task | Raised On | Prod R-Task Status | Prod OUR | Raised On | Prod OUR Status | Prod Service Request | Raised On | Prod SR Status | File Type | Prod File R-Task | Raised On | Prod File R-Task Status | IAM | Ownership Identified | Frequency | CAB Date | CAB Status | Code Review Date | Code Review Status | Code Review Invite | CR Invite Status | Release Status | Validation / Notes
ALLOCATIONS | Abishek <amuralidharan@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [8 empty] | Completed | [45 empty] | 2026-07-10
AR80 | Subash <sbandari@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [8 empty] | Yet to start | [45 empty] | 2026-07-10
BI80 | Ishan <ibhattacharjee@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [54 empty] | 2026-07-10
CBP | Shrinath <smuralikrishna@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [54 empty] | 2026-07-10
CI | Abishek <amuralidharan@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [8 empty] | Yet to start | [45 empty] | 2026-07-10
CI_MART | Subash <sbandari@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [8 empty] | Completed | [45 empty] | 2026-07-10
Ecosys | Ishan <ibhattacharjee@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [54 empty] | 2026-07-10
EDDS | Shrinath <smuralikrishna@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [54 empty] | 2026-07-10
EPM_BALANCES | Abishek <amuralidharan@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [54 empty] | 2026-07-10
EPM_DIM_NOD | Subash <sbandari@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [54 empty] | 2026-07-10
EPM_UI PUSH | Ishan <ibhattacharjee@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [54 empty] | 2026-07-10
AUDIT REPORTS | Shrinath <smuralikrishna@randomtrees.com> | Sprint 17 |  |  |  |  | 2026-07-29 | 2026-08-11 | 2026-09-11 | [54 empty] | 2026-07-10
FIN | Abishek <amuralidharan@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
FINDET_BUDGETS | Subash <sbandari@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
FINREC | Ishan <ibhattacharjee@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
FOF_WORKIVA | Shrinath <smuralikrishna@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
GL80 | Abishek <amuralidharan@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
IKW | Subash <sbandari@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
P2P | Ishan <ibhattacharjee@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
PC80 | Shrinath <smuralikrishna@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
PO80 | Abishek <amuralidharan@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
PSTREE_EPM | Subash <sbandari@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
RAS | Ishan <ibhattacharjee@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
Real_Estate | Shrinath <smuralikrishna@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
SECURITY | Abishek <amuralidharan@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
TELECOM_MICROWAVE | Subash <sbandari@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25 | [41 empty] | Blocked
TRIAD | Ishan <ibhattacharjee@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25 | [41 empty] | Blocked
UIBUDGETS | Shrinath <smuralikrishna@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
IKW_DWMS | Abishek <amuralidharan@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25
LED | Subash <sbandari@randomtrees.com> | Sprint 18 |  |  |  |  | 2026-08-12 | 2026-08-25 | [9 empty] | Yet to start
UI_PLANNER | Ishan <ibhattacharjee@randomtrees.com> | Sprint 19 |  |  |  |  | 2026-08-26 | 2026-09-08 | [9 empty] | Yet to start
FEL | Shrinath <smuralikrishna@randomtrees.com> | Sprint 19 |  |  |  |  | 2026-08-26 | 2026-09-08
Claims_Portal | Abishek <amuralidharan@randomtrees.com> | Sprint 19 |  |  |  |  | 2026-08-26 | 2026-09-08
DWMR_DM | Subash <sbandari@randomtrees.com> | Sprint 19 |  |  |  |  | 2026-08-26 | 2026-09-08
MISO | Ishan <ibhattacharjee@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
Pasta | Shrinath <smuralikrishna@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
GADS | Abishek <amuralidharan@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
GENMART | Subash <sbandari@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
TELECOM_CEB | Ishan <ibhattacharjee@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
TPD | Shrinath <smuralikrishna@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
FIELD_MOBILITY | Abishek <amuralidharan@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
Conformed_Dimensions | Subash <sbandari@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
Maximo_EDW-TDC | Ishan <ibhattacharjee@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
geoAMPS | Shrinath <smuralikrishna@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
webtrader_prj | Abishek <amuralidharan@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
FACILITY | Subash <sbandari@randomtrees.com> | Sprint 20 |  |  |  |  | 2026-09-09 | 2026-09-22
EDDS_PQ | Ishan <ibhattacharjee@randomtrees.com> | Sprint 21 |  |  |  |  | 2026-09-23 | 2026-10-06
EDDS_REL | Shrinath <smuralikrishna@randomtrees.com> | Sprint 21 |  |  |  |  | 2026-09-23 | 2026-10-06
PDS | Abishek <amuralidharan@randomtrees.com> | Sprint 21 |  |  |  |  | 2026-09-23 | 2026-10-06
DER | Subash <sbandari@randomtrees.com> | Sprint 21 |  |  |  |  | 2026-09-23 | 2026-10-06
MYACCESS | Ishan <ibhattacharjee@randomtrees.com> | Sprint 21 |  |  |  |  | 2026-09-23 | 2026-10-06
MYACCESS | Shrinath <smuralikrishna@randomtrees.com> | Sprint 22 |  |  |  |  | 2026-10-07 | 2026-10-20
TGIS | Abishek <amuralidharan@randomtrees.com> | Sprint 22 |  |  |  |  | 2026-10-07 | 2026-10-20
Maximo_EDW-TPC | Subash <sbandari@randomtrees.com> | Sprint 22 |  |  |  |  | 2026-10-07 | 2026-10-20
Maximo_EDW_CDC | Ishan <ibhattacharjee@randomtrees.com> | Sprint 22 |  |  |  |  | 2026-10-07 | 2026-10-20
DSTRACK | Shrinath <smuralikrishna@randomtrees.com> | Sprint 22 |  |  |  |  | 2026-10-07 | 2026-10-20
RAT | Abishek <amuralidharan@randomtrees.com> | Sprint 22 |  |  |  |  | 2026-10-07 | 2026-10-20
SDR | Subash <sbandari@randomtrees.com> | Sprint 22 |  |  |  |  | 2026-10-07 | 2026-10-20
SOE | Ishan <ibhattacharjee@randomtrees.com> | Sprint 22 |  |  |  |  | 2026-10-07 | 2026-10-20
TCA | Shrinath <smuralikrishna@randomtrees.com> | Sprint 22 |  |  |  |  | 2026-10-07 | 2026-10-20
Formulas:
Effective Sprint End = IF(ISNUMBER([Sprint End]),[Sprint End],IF(ISNUMBER([INPUTS - type dates]),WORKDAY([INPUTS - type dates],SprintWorkingDays-1),IF(ISNUMBER([AUDIT - Excel fills]),WORKDAY([AUDIT - Excel fills],SprintWorkingDays-1),"")))
READY / READINESS = IF(NOT(ISNUMBER([AUDIT - Excel fills])),"",WORKDAY([AUDIT - Excel fills],ReadyOffsetWD))
Sprint Readiness Date = IF(NOT(ISNUMBER([AUDIT - Excel fills])),"",WORKDAY([AUDIT - Excel fills],SprintReadinessOffsetWD))
DEV DB REQUESTS = IF(NOT(ISNUMBER([Dev OUR])),"",WORKDAY([Dev OUR],RTSKOffsetFromOUR_WD))
Dev OUR = IF(NOT(ISNUMBER([Dev Service Request])),"",WORKDAY([Dev Service Request],OUROffsetFromSR_WD))
Dev Service Request = IF(NOT(ISNUMBER([AUDIT - Excel fills])),"",WORKDAY([AUDIT - Excel fills],SROffsetFromStartWD))
RELEASE GOVERNANCE = IF(OR(NOT(ISNUMBER([Effective Release Date])),AND(WEEKDAY([Effective Release Date],2)<>2,WEEKDAY([Effective Release Date],2)<>4)),"",WORKDAY([Effective Release Date],CABOffsetFromReleaseWD))

## Sprints
Sprint # | Sprint Start | Sprint End
SPRINT 13 | 2026-06-03 | 2026-06-16
SPRINT 14 | 2026-06-17 | 2026-06-30
SPRINT 15 | 2026-07-01 | 2026-07-14
SPRINT 16 | 2026-07-15 | 2026-07-28
SPRINT 17 | 2026-07-29 | 2026-08-11
SPRINT 18 | 2026-08-12 | 2026-08-25
SPRINT 19 | 2026-08-26 | 2026-09-08
SPRINT 20 | 2026-09-09 | 2026-09-22
SPRINT 21 | 2026-09-23 | 2026-10-06
SPRINT 22 | 2026-10-07 | 2026-10-20
SPRINT 23 | 2026-10-21 | 2026-11-03

## Config (hidden)
Lead-time parameters - change yellow values only
Parameter | Value | Meaning | Status list | File types | Frequency | IAM | Yes/No | PM Name | PM Email | PM Name & Email
SprintWorkingDays | 10 | Working days in a sprint when one side is blank (2-week default). | Yet to start | MP | Daily at 5:00 AM | Yes | Yes | Abishek | amuralidharan@randomtrees.com | Abishek <amuralidharan@randomtrees.com>
ReadyOffsetWD | -1 | Working days from Effective Sprint Start to Ready By. Monday start -> previous Friday. | In Progress | FTP | Weekly (Mon at 12:00 AM) | No | No | Subash | sbandari@randomtrees.com | Subash <sbandari@randomtrees.com>
SROffsetFromStartWD | -5 | Sprint start -> Service Request raise-by. Monday start -> previous Monday. | Blocked | Fileshare | Weekly (Thursday at 12:00 AM) | N/A |  | Ishan | ibhattacharjee@randomtrees.com | Ishan <ibhattacharjee@randomtrees.com>
OUROffsetFromSR_WD | -1 | Service Request date -> OUR raise-by. SR Monday -> previous Friday. | Completed | API | Monthly (1st Monday at 4:00 AM) |  |  | Shrinath | smuralikrishna@randomtrees.com | Shrinath <smuralikrishna@randomtrees.com>
RTSKOffsetFromOUR_WD | -2 | OUR -> R-Task. OUR Friday -> previous Wednesday (VP extra buffer). |  | N/A | Yearly
CABOffsetFromReleaseWD | -1 | Release -> CAB. Thu -> Wed; Tue -> Mon. |  |  | Adhoc (on demand)
CodeReviewCalendarDays | 2 | Calendar days before CAB; weekend snaps to previous Friday. |  |  | N/A
CodeReviewInviteCalendarDays | 4 | Calendar days before Code Review to send invite email.
Yellow cells are editable. Sheet is protected so formulas cannot be overwritten. Review > Unprotect Sheet if you must change structure (no password). Sequence: R-Task -> OUR -> Service Request. Releases Tue/Thu only. CAB Mon/Wed/Fri.
SprintWarningDays | 10 | Days before Effective Sprint Start to warn if requests not actioned.
SprintReadinessOffsetWD | -2 | Working days from Effective Sprint Start to sprint-readiness discussion.